## Sheet1
|  | QUALITY ASSURANCE PLAN | [7 empty] | QAP Ref : | QEW/QAP/BUCKET
|  | Model |  | BL200 - 1 | [5 empty] | Page | 01 Of 03
BEML LIMITED, EM Division |  | Part No. |  | 375LL02114 | [5 empty] | Issue No. | 1
KGF Complex |  | Part Name |  | BUCKET 1.7 Cu. M | [5 empty] | Date : | 2023-09-23
SL.NO | COMPONENTS /OPERATIONS | CHARACTERISTICS TO BE ASSESSED |  | TYPE OF CHECK | QUANTUM OF CHECK | REFERENCE STANDARD OR DOCUMENTS | ACCEPTANCE NORMS | FORMAT OF RECORD | INSPECTION SCOPE |  |  | REMARKS
[9 empty] | SUPPLIER/MFG FIRM | BEML
1 | RAW MATERIALS & CONSUMABLES
1.1 | 1.Plates | Chemical composition |  | Chemical analysis | One sample / Heat No. | Drawing / company standard | Shall confirm to drawing / company standard | Mill certificate / NABL Report | P | R
|  | Mechanical test: UTS, Yield strength & % Elongation |  | Mechanical test
|  | Visual and dimensions |  | Visual & Measuring instruments | As per sampling plan | Drawings | Shall confirm to drawing | Inspection report | P | R
1.2 | Consumables - Welding wire / coil, paint | (i) Make & Brand (ii) Chemical (iii) Batch Code (v) Mfg & Exp. date |  | Visual | As per sampling plan | company standard | Shall confirm to drawing / company standard | TC / COC from OEM | P | R
2 | WELDING ASPECTS
2.1 | WPS & PQR for welding of steel | Procedure /Records |  | Verification | Each batch | ASME Sec IX / AWS D1.1 | ASME Sec IX / AWS D1.1 | WPS / PQR | P | R
2.2 | WPQ / WOPQ for welding of steel | Welder test certificate / welder card | [5 empty] | WPQ/ WOPQ | P | R
|  | QUALITY ASSURANCE PLAN | [7 empty] | QAP Ref : | QEW/QAP/BUCKET
|  | Model |  | BL200 - 1 | [5 empty] | Page | 02 Of 03
BEML LIMITED, EM Division |  | Part No. |  | 375LL02114 | [5 empty] | Issue No. | 1
KGF Complex |  | Part Name |  | BUCKET 1.7 Cu. M | [5 empty] | Date : | 2023-09-23
SL.NO | COMPONENTS /OPERATIONS | CHARACTERISTICS TO BE ASSESSED |  | TYPE OF CHECK | QUANTUM OF CHECK | REFERENCE STANDARD OR DOCUMENTS | ACCEPTANCE NORMS | FORMAT OF RECORD | INSPECTION SCOPE |  |  | REMARKS
[9 empty] | SUPPLIER/MFG FIRM | BEML
3 | IN PROCESS
3.1 | Plate cutting (Laser/CNC/Plasma) | Dimensions /Finish |  | Visual & Measuring instruments | 1 st item | Drawings | Shall confirm to drawing | Nesting plan | P | R
4 | MACHINING
4.1 | Machining | Visual and dimensions |  | Visual & Measuring instruments | As per sampling plan | Drawings | Shall confirm to drawing | Inspection report | P | R
5 | FINAL FABRICTION
5.1 | Weld set up | Usage of Calibrated jigs / Fixture & Set-up dimensions |  | Measure | 100% | Drawings / Standards | Drawings / Standards | Inspection report , calibration report | P | R
5.2 | Welding | Weld type, Sizes & finish |  | measure & Visual | 100% | Drawings / Standards | Drawings / Standards | Inspection report | P | R
5.3 | Weld quality | DP |  | Visual/Test | 100% | QY1027 - C Medium class | Free from weld defects | Inspection report | P | R
5.4 | Critical mounting surface | Star marked area in the drawing, machined surfaces, surfaces with drill holes |  | Visual | 100% | Drawing | Free from wel spatters/damage marks | Inspection report | P | R
5.5 | Dimension & Geometrical parameters | Mounting hole pitch,reference dimensions & Straightness, parallelism concentricity |  | Measure | 100% | Drawing/Standard | Drawing / Standard | Inspection report | P | R
6 | SURFACE TREATMENT
6.1 | Painting process : 2 coats of Primer & 1 coat of finish paint | Scratch test & DFT (Dry film thichness ) |  | Measure | 100% | As per Company Standard PWP,PR1031-C (PF, PR1032 - C) |  | Paint inspection report | P | R
7 | IDENTIFICATION Marking & Preservation / Packing
|  | QUALITY ASSURANCE PLAN | [7 empty] | QAP Ref : | QEW/QAP/BUCKET
BEML LIMITED, EM Division |  | Model |  | BL200 - 1 | [5 empty] | Page | 03 of 03
|  | Part No. |  | 375LL02114 | [5 empty] | Issue No. | 1
KGF Complex |  | Part Name |  | BUCKET 1.7 Cu. M | [5 empty] | Date : | 2023-09-23
SL.NO | COMPONENTS /OPERATIONS | CHARACTERISTICS TO BE ASSESSED |  | TYPE OF CHECK | QUANTUM OF CHECK | REFERENCE STANDARD OR DOCUMENTS | ACCEPTANCE NORMS | FORMAT OF RECORD | INSPECTION SCOPE |  |  | REMARKS
[9 empty] | SUPPLIER/MFG FIRM | BEML
7.1 | Verification of Configuration List / BOM |  |  | Visual | 100% | As per Drawing |  |  | P | W
7.2 | Preservation/ Packing | Application of Rust preventive on machined surface/ adequate packing |  | Visual | 100% | Standard practice of packing | Free from rust formation and damages,bending / distortion during transit | Inspection report | P | w
7.3 | Traceability | Identification of component |  | Visual | 100% | Standard practice of traceability | Punching /etching of Part number, vendor code, Sl. No. date of manufacture | Inspection report | P | w
ABBREVATIONS |  | TC – Test Certificate; COC – Certificate Of Conformance; P – Perform; UTS – Ultimate Tensile Strength ; RT – Radiographic Test ; DPT – Dye Penetrant Test ; R – Review; W – Witness; OEM – Original Equipment manufacturers; Mfg & Exp date – Manufacturing & Expiry Date ; WPS – Welding Procedure Specification. PQR–Procedure Qualification Record ; WPQ / WOPQ– Welder/Welding Operator Performance Qualification.
Note: 1. This Quality Assurance Plan is applicable for this BUCKET 1.7 Cu. M TO PART No. 375LL02114 only. 2. This Quality Assurance Plan does not indicate sequence of activities. Please refer Drawing for your sequence of activities. . 3. All the machined surfaces are to be applied with rust preventive oil. 4. All the openings are to be closed by dummy covers / flanges, to avoid entry of foreign particles and rusting . 5. All the threaded portions shall be covered by thread protectors, to avoid thread damage. 6. The Vendor should always refer latest details as per PO / Drawing / standards for any additional scope requirements. 7. Inspection reports to be prepared with reference to drawing / standard & QAP.
PREPARED BY |  |  | CHECKED BY |  |  | REVIEWED BY |  |  | APPROVED BY
R.CHANDRAMOHAN Manager - Fabrication Quality |  |  | MAHESH KULKARNI DGM – Fabrication Quality |  |  | DEEPAK RAJ Senior Manager – R&D |  |  | PRASANNA KUMAR BALLAL GM - Quality Engineering