## Sheet1
|  | QUALITY ASSURANCE PLAN | [7 empty] | QAP Ref : | QEW/QAP/F FRAME
|  | Model |  | BL200 - 1 | [5 empty] | Page | 01 Of 04
BEML LIMITED, EM Division |  | Part No. |  | 376MF02074 | [5 empty] | Issue No. | 1
KGF Complex |  | Part Name |  | FRAME FRONT | [5 empty] | Date : | 2023-09-23
SL.NO | COMPONENTS /OPERATIONS | CHARACTERISTICS TO BE ASSESSED |  | TYPE OF CHECK | QUANTUM OF CHECK | REFERENCE STANDARD OR DOCUMENTS | ACCEPTANCE NORMS | FORMAT OF RECORD | INSPECTION SCOPE |  |  | REMARKS
[9 empty] | SUPPLIER/MFG FIRM | BEML
1 | RAW MATERIALS & CONSUMABLES
1.1 | 1.Plates | Chemical composition |  | Chemical analysis | One sample / Heat No. | Drawing / company standard | Shall confirm to drawing / company standard | Mill certificate / NABL Report | P | R
|  | Mechanical test: UTS, Yield strength & % Elongation |  | Mechanical test
|  | Visual and dimensions |  | Visual & Measuring instruments | As per sampling plan | Drawings | Shall confirm to drawing | Inspection report | P | R
1.2 | Bought Out-Items pads, seats | Visual and dimensions |  | Visual & Measuring instruments | As per sampling plan | Drawings / company standard | Shall confirm to drawing / company standard | Inspection report | P | R
1.3 | Consumables - Welding wire / coil, paint | (i) Make & Brand (ii) Chemical (iii) Batch Code (v) Mfg & Exp. date |  | Visual | As per sampling plan | company standard | Shall confirm to drawing / company standard | TC / COC from OEM | P | R
2 | WELDING ASPECTS
2.1 | WPS & PQR for welding of steel | Procedure /Records |  | Verification | Each batch | ASME Sec IX / AWS D1.1 | ASME Sec IX / AWS D1.1 | WPS / PQR | P | R
2.2 | WPQ / WOPQ for welding of steel | Welder test certificate / welder card | [5 empty] | WPQ/ WOPQ | P | R
|  | QUALITY ASSURANCE PLAN | [7 empty] | QAP Ref : | QEW/QAP/F FRAME
|  | Model |  | BL200 - 1 | [5 empty] | Page | 02 Of 04
BEML LIMITED, EM Division |  | Part No. |  | 376MF02074 | [5 empty] | Issue No. | 1
KGF Complex |  | Part Name |  | FRAME FRONT | [5 empty] | Date : | 2023-09-23
SL.NO | COMPONENTS /OPERATIONS | CHARACTERISTICS TO BE ASSESSED |  | TYPE OF CHECK | QUANTUM OF CHECK | REFERENCE STANDARD OR DOCUMENTS | ACCEPTANCE NORMS | FORMAT OF RECORD | INSPECTION SCOPE |  |  | REMARKS
[9 empty] | SUPPLIER/MFG FIRM | BEML
3 | IN PROCESS
3.1 | Plate cutting (Laser/CNC/Plasma) | Dimensions /Finish |  | Visual & Measuring instruments | 1 st item | Drawings | Shall confirm to drawing | Nesting plan | P | R
4 | SUB STRUCTURES FABRICATION
4.1 | Weld set up | Usage of Calibrated jigs / Fixture & Set-up dimensions |  | Measure | 100% | Drawings / Standards | Drawings / Standards | Inspection report , calibration report | P | R
4.2 | Welding | Weld type, Sizes & finish |  | measure & Visual | 100% | Drawings / Standards | Drawings / Standards | Inspection report | P | R
4.3 | Weld quality | DP/ UT |  | Visual/Test | 100% | QY1027 - C Fine class | Free from weld defects | Inspection report | P | R
4.4 | Critical mounting surface | Star marked area in the drawing |  | Visual | 100% | Drawing | Free from wel spatters/damage marks | Inspection report | P | R
5 | SUB STRUCTURES MACHINING
5.1 | Machining | Visual and dimensions |  | Visual & Measuring instruments | As per sampling plan | Drawings | Shall confirm to drawing | Inspection report | P | R
6 | FINAL FABRICTION
6.1 | Weld set up | Usage of Calibrated jigs / Fixture & Set-up dimensions |  | Measure | 100% | Drawings / Standards | Drawings / Standards | Inspection report , calibration report | P | R
6.2 | Welding | Weld type, Sizes & finish |  | measure & Visual | 100% | Drawings / Standards | Drawings / Standards | Inspection report | P | R
|  | QUALITY ASSURANCE PLAN | [7 empty] | QAP Ref : | QEW/QAP/F FRAME
|  | Model |  | BL200 - 1 | [5 empty] | Page | 03 of 04
BEML LIMITED, EM Division |  | Part No. |  | 376MF02074 | [5 empty] | Issue No. | 1
KGF Complex |  | Part Name |  | FRAME FRONT | [5 empty] | Date : | 2023-09-23
SL.NO | COMPONENTS /OPERATIONS | CHARACTERISTICS TO BE ASSESSED |  | TYPE OF CHECK | QUANTUM OF CHECK | REFERENCE STANDARD OR DOCUMENTS | ACCEPTANCE NORMS | FORMAT OF RECORD | INSPECTION SCOPE |  |  | REMARKS
[9 empty] | SUPPLIER/MFG FIRM | BEML
6.4 | Critical mounting surface | Star marked area in the drawing, machined surfaces, surfaces with drill holes |  | Visual | 100% | Drawing | Free from wel spatters/damage marks | Inspection report | P | R
7 | SURFACE TREATMENT
7.1 | Painting process : 2 coats of Primer & 1 coat of finish paint | Scratch test & DFT (Dry film thichness ) |  | Measure | 100% | As per Company Standard PWP,PR1031-C (PF, PR1032 - C) |  | Paint inspection report | P | R
8 | IDENTIFICATION Marking & Preservation / Packing
8.1 | Verification of Configuration List / BOM |  |  | Visual | 100% | As per Drawing |  | - | P | W
8.2 | Preservation/ Packing | Application of Rust preventive on machined surface/ adequate packing |  | Visual | 100% | Application of layer of preservative and packed in suitable bag / box in a manner to preclude any damages during shipment and handlings. | Standard practice of packing | Inspection report | P | w
8.3 | Traceability | Identification of component |  | Label | 100% | label with Part No and description, Affix with halogram on bin samples / Packing | Standard practice of packing | Inspection report | P | w
|  | QUALITY ASSURANCE PLAN | [7 empty] | QAP Ref : | QEW/QAP/F FRAME
|  | Model |  | BL200 - 1 | [5 empty] | Page | 03 of 04
BEML LIMITED, EM Division |  | Part No. |  | 376MF02074 | [5 empty] | Issue No. | 1
KGF Complex |  | Part Name |  | FRAME FRONT | [5 empty] | Date : | 2023-09-23
ABBREVATIONS |  | TC – Test Certificate; COC – Certificate Of Conformance; P – Perform; UTS – Ultimate Tensile Strength ; RT – Radiographic Test ; DPT – Dye Penetrant Test ; R – Review; W – Witness; OEM – Original Equipment manufacturers; Mfg & Exp date – Manufacturing & Expiry Date ; WPS – Welding Procedure Specification. PQR–Procedure Qualification Record ; WPQ / WOPQ– Welder/Welding Operator Performance Qualification.
Note: 1. This Quality Assurance Plan is applicable for this FRAME FRONT TO PART No. 376MF02074 only. 2. This Quality Assurance Plan does not indicate sequence of activities. Please refer Drawing for your sequence of activities. 3. All the machined surfaces are to be applied with rust preventive oil. 4. All the openings are to be closed by dummy covers / flanges, to avoid entry of foreign particles and rusting . 5. All the threaded portions shall be covered by thread protectors, to avoid thread damage. 6. The Vendor should always refer latest details as per PO / Drawing / standards for any additional scope requirements. 7. Inspection reports to be prepared with reference to drawing / standard & QAP.
PREPARED BY |  |  | CHECKED BY |  |  | REVIEWED BY |  |  | APPROVED BY
R.CHANDRAMOHAN Manager - Fabrication Quality |  |  | MAHESH KULKARNI DGM – Fabrication Quality |  |  | DEEPAK RAJ Senior Manager – R&D |  |  | PRASANNA KUMAR BALLAL GM - Quality Engineering