## Sheet1
|  | QUALITY ASSURANCE PLAN | [7 empty] | QAP Ref : | QEW/QAP/BRACKET ASSY
|  | Model |  | BL200 - 1 | [5 empty] | Page | 01 Of 03
BEML LIMITED, EM Division |  | Part No. |  | 376EI02092 | [5 empty] | Issue No. | 1
KGF Complex |  | Part Name |  | BRACKET ASSY FRONT | [5 empty] | Date : | 2023-09-23
SL.NO | COMPONENTS /OPERATIONS | CHARACTERISTICS TO BE ASSESSED |  | TYPE OF CHECK | QUANTUM OF CHECK | REFERENCE STANDARD OR DOCUMENTS | ACCEPTANCE NORMS | FORMAT OF RECORD | INSPECTION SCOPE |  |  | REMARKS
[9 empty] | SUPPLIER/MFG FIRM | BEML
1 | RAW MATERIALS & CONSUMABLES
1.1 | 1.Plates | Chemical composition |  | Chemical analysis | One sample / Heat No. | Drawing / company standard | Shall confirm to drawing / company standard | Mill certificate / NABL Report | P | R
|  | Mechanical test: UTS, Yield strength & % Elongation |  | Mechanical test
|  | Visual and dimensions |  | Visual & Measuring instruments | As per sampling plan | Drawings | Shall confirm to drawing | Inspection report | P | R
1.2 | Consumables - Welding wire / coil, paint | (i) Make & Brand (ii) Chemical (iii) Batch Code (v) Mfg & Exp. date |  | Visual | As per sampling plan | company standard | Shall confirm to drawing / company standard | TC / COC from OEM | P | R
2 | WELDING ASPECTS
2.1 | WPS & PQR for welding of steel | Procedure /Records |  | Verification | Each batch | ASME Sec IX / AWS D1.1 | ASME Sec IX / AWS D1.1 | WPS / PQR | P | R
2.2 | WPQ / WOPQ for welding of steel | Welder test certificate / welder card | [5 empty] | WPQ/ WOPQ | P | R
|  | QUALITY ASSURANCE PLAN | [7 empty] | QAP Ref : | QEW/QAP/BRACKET ASSY
|  | Model |  | BL200 - 1 | [5 empty] | Page | 02 Of 03
BEML LIMITED, EM Division |  | Part No. |  | 376EI02092 | [5 empty] | Issue No. | 1
KGF Complex |  | Part Name |  | BRACKET ASSY FRONT | [5 empty] | Date : | 2023-09-23
SL.NO | COMPONENTS /OPERATIONS | CHARACTERISTICS TO BE ASSESSED |  | TYPE OF CHECK | QUANTUM OF CHECK | REFERENCE STANDARD OR DOCUMENTS | ACCEPTANCE NORMS | FORMAT OF RECORD | INSPECTION SCOPE |  |  | REMARKS
[9 empty] | SUPPLIER/MFG FIRM | BEML
3 | IN PROCESS
3.1 | Plate cutting (Laser/CNC/Plasma) | Dimensions /Finish |  | Visual & Measuring instruments | 1 st item | Drawings | Shall confirm to drawing | Nesting plan | P | R
4 | FINAL FABRICTION
4.1 | Weld set up | Usage of Calibrated jigs / Fixture & Set-up dimensions |  | Measure | 100% | Drawings / Standards | Drawings / Standards | Inspection report , calibration report | P | R
4.2 | Welding | Weld type, Sizes & finish |  | measure & Visual | 100% | Drawings / Standards | Drawings / Standards | Inspection report | P | R
4.3 | Weld quality | DP |  | Visual/Test | 100% | QY1027 - C Medium class | Free from weld defects | Inspection report | P | R
4.4 | Critical mounting surface | Star marked area in the drawing,machined surfaces, surfaces with drill holes |  | Visual | 100% | Drawing | Free from welding spatters/damage marks | Inspection report | P | R
4.5 | Dimension & Geometrical parameters | Mounting hole pitch,reference dimensions & Flatness |  | Measure | 100% | Drawing/Standard | Drawing / Standard | Inspection report | P | R
5 | SURFACE TREATMENT
5.1 | Painting process : 2 coats of Primer & 1 coat of finish paint | Scratch test & DFT (Dry film thichness ) |  | Measure | 100% | As per Company Standard PWP,PR1031-C (PF, PR1032 - C) |  | Paint inspection report | P | R
6 | IDENTIFICATION Marking & Preservation / Packing
6.1 | Verification of Configuration List / BOM |  |  | Visual | 100% | As per Drawing |  | - | P | W
|  | QUALITY ASSURANCE PLAN | [7 empty] | QAP Ref : | QEW/QAP/BRACKET ASSY
|  | Model |  | BL200 - 1 | [5 empty] | Page | 03 of 03
BEML LIMITED, EM Division |  | Part No. |  | 376EI02092 | [5 empty] | Issue No. | 1
KGF Complex |  | Part Name |  | BRACKET ASSY FRONT | [5 empty] | Date : | 2023-09-23
SL.NO | COMPONENTS /OPERATIONS | CHARACTERISTICS TO BE ASSESSED |  | TYPE OF CHECK | QUANTUM OF CHECK | REFERENCE STANDARD OR DOCUMENTS | ACCEPTANCE NORMS | FORMAT OF RECORD | INSPECTION SCOPE |  |  | REMARKS
[9 empty] | SUPPLIER/MFG FIRM | BEML
6.3 | Identification Marking |  |  | Label | 100% | label with Part No and description, Affix with halogram on bin samples / Packing | Punching /etching of Part number, vendor code, Sl. No. date of manufacture | Inspection report | P | w
ABBREVATIONS |  | TC – Test Certificate; COC – Certificate Of Conformance; P – Perform; UTS – Ultimate Tensile Strength ; RT – Radiographic Test ; DPT – Dye Penetrant Test ; R – Review; W – Witness; OEM – Original Equipment manufacturers; Mfg & Exp date – Manufacturing & Expiry Date ; WPS – Welding Procedure Specification. PQR–Procedure Qualification Record ; WPQ / WOPQ– Welder/Welding Operator Performance Qualification.
Note: 1. This Quality Assurance Plan is applicable for this BRACKET ASSY FRONT TO PART No. 376EI02092 only. 2. This Quality Assurance Plan does not indicate sequence of activities. Please refer Drawing for your sequence of activities. 3. The Vendor should always refer latest details as per PO / Drawing / standards for any additional scope requirements. 4. Inspection reports to be prepared with reference to drawing / standard & QAP.
PREPARED BY |  |  | CHECKED BY |  |  | REVIEWED BY |  |  | APPROVED BY
R.CHANDRAMOHAN Manager - Fabrication Quality |  |  | MAHESH KULKARNI DGM – Fabrication Quality |  |  | DEEPAK RAJ Senior Manager – R & D |  |  | PRASANNA KUMAR BALLAL GM - Quality Engineering