## BOQ
BEML LIMITED, BANGALORE COMPLEX
RMM/TEN-6300031394/2020 Date: 27.01.2020
ISSUED TO: |  | Period of contract: |  | 03 Months
|  | EMD : |  | Rs. | 52000
SCHEDULE 'A' - BILL OF QUANTITIES
Sub:- Civil works in S-1 Hangar to establish facility for assembly of Airborne structure/ISRO activities in BEML limited, Bangalore Complex, Bangalore 560075
Sl. No | Description | Unit | Qty. | Rate/unit in figures & in words Rs. | Amount (Rs)
1 | Demolition/dismantling the existing cement concrete flooring/hard standing concrete in any description and in any position not otherwise specifically provided for etc complete all as specified and as directed by Engineer in charge. Note: The dismantled materials should be removed immediately from the premises without disturbing the regular production activities & the quoted rate includes all lead & lift etc. | Cum | 10
2 | Earthwork excavation by mechanical/ manual means in foundation trenches, pits not exceeding 1.50m in width and not exceeding 1.50m in depth and not exceeding 10 sqm on plan in Hard soil but excluding hard rock including getting out the excavated earth, dressing of sides, dewatering ground water/ rain water, compaction etc., complete all as specified and directed by Engineer in charge. | Cum | 25
3 | Earthwork excavation by manual means for post holes not exceeding 0.5 cum including getting out, returning, filling in and ramming earth or broken rubble mixed with earth alround in layers not exceeding 25 cms, watering, and removing surplus soil to a distance not exceeding 50 mtrs and making good the surface etc.,complete all as specified and as directed by the Engineer in charge. | Nos | 25
4 | Providing and laying in Position Plain cement concrete of Mix proportion 1:4:8 using 40mm down graded granite aggregate, laid in layers not exceeding 15cms well compacted for foundation, under floors and other similar works including curing etc.,complete all as specified and as directed by the Engineer in charge. | Cum | 5
5 | Providing & constructing size stone masonry in CM 1:6 using approved quality of size stones for foundation,well bonded at every 1.5 Mtrs apart solidly hearted each course well levelled etc.,complete all as specified and as directed by Engineer in charge. Note: The rate quoted is deemed to include for dressing of all the stones & corner stones. | Cum | 15
6 | Providing and constructing burnt brick masonry 230mm thick in cement mortar 1:6 using first class approved quality table moulded bricks for superstructure at required heights laid on plan, including curing, tools & tackles etc., complete all as specified and directed by the Engineer in charge. | Cum | 1
7 | Providing TMT bars (Fe 500 grade) in reinforcement conforming to relevant IS in various diameter for various location & levels, cut to length & bent to required shape, binding spirally with MS wire (annealed) of size not less than 0.9mm dia and placing in position including all lead, lift, labour, tools & tackles, plants & machinery etc complete all as specified and as directed by Engineer in charge. Note: a) The rate quoted is deemed to include for providing cement mortar cover blocks as per the requirement at site. b) Reinforcement shall be measured based on actual quantity placed in position on standard weight basis & no allowance shall be made for rolling margin c) only authorised laps, chairs & spacers shall be measured & paid. | Kgs | 5000
8 | Supplying, Fabricating, hoisting and erecting in position MS Structural steel frame works for purlins & columns of wall cladding using MS Structural steel like ISMC, MS plates, MS angles, flats including cutting, welding, bending to required shape bolting, cleaning the rust and scales to the satisfication of Engineer in charge. Shims & packing pieces will be required for levelling of the work for erection at all elevations, levels & heights etc.,complete all as specified and as directed by Engineer-in-charge. Note: The quoted rate is deemed to include for labour, welding machines, gas, electrodes and all consumables required for the work etc., | Kgs | 3000
9 | Supplying fixing & installation of M/s. JSW/TATA make single skin HI-Rib trapezoidal profile PPGL colour coated (sky blue/approved colour) sheeting 1060mm supply width, minimum 1000mm covered width 29mm-30mm crest height, 24mm crest width with 195-200mm pitch in 0.50mm thick TCT at required length (55% aluminum-43%Zinic Coating) 150 GSM with 550 Mpa minimum tensile strength conforming to IS277, Alloy Coated conforming to AS 1397 for wall cladding etc inclusive of all transportation charges, taxes & levies, & including all fixtures like colour matched nylon head self tapping corroision protected mechanically galvanised fasteners with integral washer etc , complete all as specified and as directed by Engineer in charge. Note: The finished/covered sheet area excluding lap only shall be measured and paid. | Sqm | 340
10 | Supplying & fixing 20 mm dia MS threaded bolts of required length for the column base plate including hexagonal nuts etc., complete as specified and directed by Engineer in charge | Kgs | 25
11 | Supplying, Fabricating, hoisting and erecting in position MS Structural steel works for stair case, hand rails using MS Structural steel like MS angles, MS Pipes & flats including cutting, welding, bending to required shape bolting, cleaning the rust and scales to the satisfication of Engineer in charge, etc.,complete all as specified and as directed by Engineer in charge. Note: The quoted rate is deemed to include for labour, welding machines, gas, electrodes and all consumables required for the work etc., | Kgs | 150
12 | Carting away unwanted and unusable excavated soil,debris & dumping at a place shown in township area at a distance not exceeding 5.0KM including all lead and lift, transportation etc., complete all as specified and as directed by Engineer in charge. | Cum | 30
13 | Providing and laying in position Plain cement concrete of mix proportion 1:2:4 using 20mm down graded granite aggregate, for hard standing concrete, 150mm thick in chess board pattern or as per site conditions, finishing with wooden float, laid in layers, well compacted, machine mixed, including curing, providng & removal of centering / shuttering if required as per site conditions, finishing the surface smooth & even etc.,complete all as specified and as directed by Engineer in charge. | Sqm | 30
14 | Preparing the steel surfaces by scrapping, sand papering & applying two coats of synthetic enamel paint over a coat of redoxide Primer of first quality approved colour manufactured by M/s. Asian Paints/Berger including lead, lift, materials, labour, tools & tackles, etc.,complete all as specified and as directed by Engineer in charge. | Sqm | 100
15 | Providing and laying in position Reinforced Cement Concrete in mix proportion 1:1.5:3 of M20 grade for footings, pedestals, plinth beams, RCC roof slab, stair case, platform using 20mm down graded granite aggregates,mechanical mixing and placing at all levels, vibrating, consolidating, curing and finishing including labours, lead, lift, tools, plant & machinery, hire & fuel charges & all other incidental charges etc.,complete all as specified and as directed by Engineer in charge.
| a) RCC Footings & Pedestals | Cum | 4
| b) RCC Plinth beams | Cum | 3
| c) RCC Columns, lintels | Cum | 5
| d) RCC roof slab | Cum | 10
| e) RCC Stair case and landings | Cum | 3
| f) RCC Platform | Cum | 8
16 | Providing, erecting and removal of leak proof formwork for RCC works etc (Centring and shuttering including strutting, propping etc) using MS/ plywood, conforming to relevant IS with necessary wooden formwork supports, metal propping, MS pipe ties, bracings, staging, applying of chemical releasing agent to MS/plywood surfaces to avoid sticking of cement so as to have a smooth finish at all levels while casting the concrete member of any shape, size and thickness etc complete all as specified and directed by Engineer-in- charge. | Sqm | 210
17 | Providing Rendering/Plastering for the concrete / masonary surfaces in cement mortar of mix proportion 1:4, 15mm thick including tools & tackles, scaffolding, curing etc., complete as specified and directed by Engineer in charge. | Sqm | 180
18 | Providing and installing anodise aluminium glazed partitions with outer frame verticals and horizontal members made out of powder coated aluminium extrusions of Jindal/Hindal or equivalent make conforming to I.S comprising of aluminium extruded rectangular hollow tubes measuring not less than 63.1mm x 38.10mm x 1.5mm outer frame, intermediate, verticals and horizontals at 100cms Centers approx. and the panel top member and bottom member.Bottom panel nearly 1m height from floor level fixed with 12mm thick pre-laminated particle board flat pressed three layer or graded wood particle board conforming to IS and of reputed manufacturer like Archid/ LEO/National/Greenply, termite resistant quality etc., balance panels fixed with 5mm thick plain / opaque glass / pinhead glass of approved quality MODIGUARD / SAINT GOBAIN make, conforming to I.S Superior quality rubber glazing gaskets and aluminium tapered glazing clips 0.7mm thick and measuring (19 x 17) mm self interlocking screwless, snap on type for fixing particle board / glazing, etc as per site conditions. | Sqm | 210
Note: (1) The aluminium sections mentioned for frame, horizonal, vertical & intermediate members are only approx. sizes and could be changed as per site conditions & with prior approval of BEML (2) The height of pre-lam paticle board or graded wood board mentioned is also approx and could be changed as per site conditions with prior approval of BEML
19 | Providing and fixing partly paneled and partly glazed single leaf Openable door with frame of aluminium extruded rectangular hollow tubes made from high grade HE 9W.P alloy ‘JINDAL’ or ‘INDAL’ comprising of aluminium top, middle and side members of size 47.62mm x 44.45 x 1.5mm, bottom member shall measure of size 104.30mm x 44.45mm x 1.5mm, Bottom panel approx. 1m height fixed with 12mm thick prelaminated particle board flat pressed three layer or graded wood particle board conforming to IS and balance panels provided with 5mm thick translucent/opaque glass of IS approved quality MODIGUARD / SAINT GOBAIN make, conforming to I.S with superior quality rubber glazing gaskets and aluminium tapered glazing clip measuring (19mm x 17mm) self interlocking, screw less, snap-on type for fixing glass. The door shall have all necessary hardware & accessories like handles, locking arrangement, floor spring of reputed manufacturer like Dorma/Everite/Hardwyn etc as per site conditions | Sqm | 11
Note: (1) The aluminium sections mentioned for frame, horizonal, vertical & intermediate members are only approx. sizes and could be changed as per site conditions & with prior approval of BEML (2) The height of pre-lam paticle board or graded wood board mentioned is also approx and could be changed as per site conditions with prior approval of BEML
20 | Providing and fixing Saint Gobain Gyproc 12.5mm Tiled false ceiling in true horizontal level suspended on inter locking Gyproc Matrix metal grid of hot dipped galvanized steel sections. PPGI wall angle 24x24x0.4mm is fixed along the perimeter of ceiling to walls. 1200mm x 1200mm grid Main “T” runners (Materials-GI(IS513), YS-260Mpa, Finish-Galvanised 120GSM (IS277) are then suspended from ceiling using 4mm GI adjustable rods with Galvanised butterfly level clips of size 85 x 30 x 0.8mm/required material as per site conditions to be used spaced at max 1200mm centre to centre along main T and not more than 150mm for spliced joints. The last hangar at the end of each main runner should not be greater than 600mm from the adjacent wall. 1200mm long cross T (Material-GI(IS513), YS-260Mpa, Finish-Galvanised 120 GSM(IS 277) is interlocked between the main T at 600 mm c/c to form a grid of 1200x600 mm and than secondary cross “T” (Material-GI(IS513), YS-260Mpa, Finish-Galvanised 120GSM(IS277)) of length 600mm is than interlocked at middle of the 1200x600mm grid to form grids of 600x600mm. Cross Tees at the ends having length more than 600mm are to be supported independently. Finally 12.5mm thick Gyproc gypsum tile of size 595x595mm is placed in grid. | Sqm | 60
21 | Preparing the surface of internal ceiling/walls by scrapping, sand papering, including necessary repairs to cracks, scratches and cleaning the surface from dust, dirt and filling/closing the cracks with crack filling compound and applying two coats of Oil bound distemper over a coat of primer and putty of first quality approved brand and colour manufactured by M/s.Asian Paints/Berger paints etc., complete all as specified and as directed by Engineer in charge. Note.Contractor's quoted rate is deemed to include for providing and removal of scaffolding/ suspending jhoola for painting. | Sqm | 180
22 | Returning & filling the available earth in plinth, trenches, ducts, pits, foundations or around plinth with approved earth of non swelling type, free from organic materials, consolidating in layers of not more than 200mm thickness including watering, compaction, etc complete all as specficed and as directed by Engineer in charge. Note:Net consolidated volume only shall be measured for payment purposes. | Cum | 10
23 | Supplying and fixing new 5.5 mm thick plain sheet glass of first quality manufactured by M/s. Saintgobain for the window panes, fixed & secured firmly to the window frames with all necessary hardware etc., complete all as specified and directed by Engineer in charge. | Sqm | 5
24 | Supplying & fixing of GI Chainlink fence 100GSM MICON, Rust resistant 10G (2.9 to 3mm dia) with 50mm x 50mm size openings including transportation, loading, unloading with all necessary hardware etc., complete all as specified and directed by Engineer in charge. | Sqm | 180
25 | Supplying, installation, testing & commissioning of access control for One entrance door with biometric readers and accessories viz., 2nos bio metric readers, EM Lock with exit switch-1no., personalisation + Enrollment reader, software, required length of network cables, power cables, signal cables, casing and capping, port switch etc., complete all as specified & directed by the Engineer-in-charge | LS | 1
| Total Amount excluding GST |  |  | Rs.
| GST Amount |  |  | Rs.
| Total Amount inclusive of GST |  |  | Rs.
TOTAL AMOUNT IN WORDS: RUPEES
NOTE:
(1) The contractors/prospective bidders are requested to visit the site and aquaint themselves with the site conditions before submission of bid
(2) The labour employed for the work should be covered under ESI & PF
(3) The work has to be carried out by the Contractor under the supervision of the Contractor himself or under the supervision of a qualified technical personnel employed by the Contractor till the completion of the work
(4) The Contractor to note that the dismantled materials should be removed and shifted immediately from the site premises without disturbing the regular activities in the hangar/ adjoining areas and the rate is deemed to include for the same
(5) The work has to be carried out without causing hindrance to the regular material movement at the proposed site
| Authorised Signatory |  | Signature of the Contractor
| Purchase Dept. |  | With seal